## Slide 1: METADATA
DOCUMENT: Q1 2025 Platform Engineering Quarterly Business Review
TOPIC: QBR, Quarterly Review, Performance, Incidents, Capacity, Roadmap, Budget, KPIs
VERSION: 1.0
LAST UPDATED: 2025-04-10
OWNER: Platform Engineering Lead
SOURCE_FORMAT: PowerPoint Presentation

## Slide 2: SLIDE 1 — Q1 2025 Executive Summary
Quarter in Review: January – March 2025
RELIABILITY:
Total incidents: 4 (vs 10 in 2024 full year — trending well)
SEV-1: 0. SEV-2: 1 (INC-2025-0203 — Fraud Engine NaN scores).
Total downtime: 230 min (SEV-2 only). Target: <200 min/year.
AUTH-SVC: 100% uptime for 6 consecutive months.
CAPACITY:
PAYMENTS-GW approaching TPS ceiling (500 TPS). Horizontal scale in progress (May 2025).
FRAUD-ENGINE peak CPU 94% — Redis auto-scaling and GPU evaluation underway.
CBS Oracle DB on track for 80% capacity May 2026 — partitioning study scheduled Q3 2025.
RELEASES:
12 releases in Q1 2025. 1 rollback (REL-2025-009 — Fraud Engine NaN bug).
Post-rollback: automated null-rate gate added to deployment pipeline.
BUDGET:
Q1 capex/opex within budget. Snowflake DWH cost trending 8% above budget — optimisation needed.
SLA credits issued: $5,400 (Dec 2024 breaches). No Q1 2025 credits issued.

## Slide 3: SLIDE 2 — Incident Deep Dive Q1 2025
INC-2025-0044 (Jan 31, SEV-3, 18 min) — Kafka Broker-2 disk space
Root cause: Log segment accumulation. Addressed by Kafka 3.5.1 upgrade (REL-2025-007).
Customer impact: None. Auto-recovered.
INC-2025-0112 (Feb 18, SEV-3, 12 min) — AUTH-SVC token refresh edge case
Root cause: Edge case in token refresh for accounts with expired MFA devices.
Impact: ~50 users required re-authentication.
Fix: Deployed in REL-2025-011 (AUTH-SVC v1.5.1).
INC-2025-0203 (Mar 14, SEV-2, 167 min) — FRAUD-ENGINE NaN fraud scores
Root cause: REL-2025-009 (v3.3.0) introduced NULL merchant_category_code handling bug.
NaN comparison with fraud threshold evaluated to False — transactions bypassed fraud check.
Impact: 1,800 transactions without fraud scoring. 3 confirmed fraud. $4,200 exposure.
Recovery: Rolled back to v3.2.1. v3.3.1 with fix deployed Mar 20.
Prevention: Fraud score null-rate automated deployment gate added.
Lesson: Deployment gates are more reliable than manual QA for statistical anomalies.
INC-2025-0288 (Apr 2, SEV-3, 33 min) — REPORTING-SVC slow query
Root cause: Missing index on DWH fact_transactions table (new column from CBS v4.2.0).
Impact: Report generation 4x slower — no SLA breach.
Fix: Index added by DBA team. Added DWH index check to CBS release checklist.

## Slide 4: SLIDE 3 — Capacity and Performance Q1 2025
PAYMENTS-GW:
Peak TPS Q1: 412 (Feb month-end). Ceiling: ~500 TPS.
Horizontal scale (v2.9.0) planned May 15 — will raise ceiling to ~1,000 TPS.
Peak CPU: 88% (still WARNING status). Urgency: HIGH.
FRAUD-ENGINE:
Peak CPU: 94% — highest across all services (WARNING).
Redis auto-scaling in progress (completion May 2025).
GPU offload benchmarking: Q3 2025. Expected CPU reduction to <30% if adopted.
CBS Oracle DB:
Current size: 1,904 GB (grew +64 GB in Q1 — +22 GB/month average).
Projected 80% capacity: May 2026. DBA partitioning study scheduled Q3 2025.
Snowflake DWH:
Q1 compute cost: $52,400 (8% above quarterly budget of $48,500).
Cause: Three large ad-hoc analytics queries from BI team without query optimisation.
Action: Query governance policy tightened. Cost monitoring dashboard created.
AUTH-SVC:
Avg CPU: 18%, Peak: 44% — well within capacity. Healthy.
Token caching (grace period) implementation in progress — target Q2 2025.

## Slide 5: SLIDE 4 — Roadmap Status Q1 2025
COMPLETED in Q1:
[DONE] CBS v4.2.0 — DB pool size 50→100, bulk payment API, enhanced audit logging
[DONE] Kafka v3.5.1 upgrade — zero-downtime rolling upgrade
[DONE] ETL schema pre-flight validation — eliminates silent schema mismatch failures
[DONE] Automated fraud score null-rate deployment gate
[DONE] SWIFT ISO 20022 infrastructure ready (activation Q3 2025)
IN PROGRESS (Q2 targets):
[65%] PAYMENTS-GW horizontal scale — LB config in progress, session state refactor pending
[40%] Fraud Engine Redis auto-scaling — Sentinel config complete, load testing next
[20%] AUTH-SVC token caching (grace period) — design done, implementation starting
[10%] Vault secrets integration — Auth-SVC first, others to follow
AT RISK:
Containerisation Phase 1 (Q3) — K8s cluster provisioning delayed 3 weeks.
Service mesh PoC (Q3) — engineer bandwidth constrained. May slip to Q4.
UPCOMING Q2 RELEASES:
May 8: FRAUD-ENGINE v3.4.0 (new ML model v4.0.0)
May 15: PAYMENTS-GW v2.9.0 (horizontal scale support)
May 22: REPORTING-SVC v2.0.0 (Basel III LCR new format)

## Slide 6: SLIDE 5 — Budget and Cost Summary Q1 2025
Q1 2025 Technology Spend:
Snowflake DWH: $52,400 (budget: $48,500 — 8% OVER)
Datadog APM: $10,500 (in line)
IBM QRadar: $24,000 (in line)
AWS Cloud Services: $2,100 (in line)
PagerDuty: $3,600 (in line)
Oracle support: $21,000 (in line)
SWIFT membership: $30,000 (in line — quarterly tranche)
Confluent Control: $4,500 (in line)
TOTAL Q1: $148,100 (budget: $144,000 — 2.8% OVER)
Cost optimisation actions:
1. Snowflake query governance — target 10% cost reduction Q2
2. Confluent renewal review — evaluate vs open-source alternatives (savings: $18K/yr)
3. PagerDuty user audit — 12 users have not been on-call in 90 days
Q2 forecast: $147,000 (slightly under Q1 if Snowflake optimisation works)
CapEx request for Q3:
K8s cluster hardware: $42,000 (on-prem servers for container workloads)
GPU server for Fraud Engine evaluation: $18,000 (pending benchmark results)